## Dashboard
API Testing Project Dashboard
Project Name | API testing
Delivery Date | 24/07/2025
Release Number | Release no 01
Designed By | Nagham,Hala.Foqahaa,Badawi,Ehab
Android Versions | -
iOS Versions | -
Total Number of Test Cases | 118
Number of Passed Test Cases | 100
Number of Failed Test Cases | 18
Number of Blocked Test Cases | 0
Environment | Postman

## Test Cases (User)
Test Suite ID | Test Suite Title | Test Case ID | Summary | Method | Request Body | Scripts | Reproduce Steps | Expected Result | Actual Result | Status | Bug. ID
TS-USER-01 | Add User | TC-USER-01-01 | Verify user registration with valid data | POST | { "firstName": "John", "email": "john@example.com" } | pm.test("Status code is 201", function () { pm.response.to.have.status(201); }); | 1. Open Postman 2. Send POST request to /users with valid payload | Status 201 Created. | As Expected | PASS | —
|  | TC-USER-01-02 | Register user with missing required field | POST | { "firstName": "Test", "lastName": "User", "email": "Nagham2293900@gmail.com" } | pm.test("Status code is 400", function () { pm.response.to.have.status(400); }); | 1. Open Postman 2. Send POST to /users with missing password | Status 400 Bad Request. | As Expected | PASS | —
|  | TC-USER-01-03 | Register with already registered email | POST | Same as TC-USER-01 | pm.test("Status code is 409 or 400", function () { pm.expect(pm.response.code).to.be.oneOf([400, 409]); }); | 1. Open Postman 2. Send POST to /users again with the same email | Status 400 Bad Request. Error message indicating duplicate email | As Expected | PASS | —
|  | TC-USER-01-04 | Validate response time is less than 700ms | POST | Same as TC-USER-01 | pm.test("Response time is less than 700ms", function () { pm.expect(pm.response.responseTime).to.be.below(700); }); | 1. Open Postman2. Send POST request | Response time is less than 700ms | As Expected | PASS | —
|  | TC-USER-01-05 | Send request to incorrect URL | POST | Same as TC-USER-01 | pm.test("Status code is 404 or 503", function () { pm.expect(pm.response.code).to.be.oneOf([404, 503]); }); | 1. Open Postman2. Send POST to incorrect endpoint /user | Status 404 Not Found or 503 Service Unavailable | As Expected | PASS | —
|  | TC-USER-01-06 | Verify the status of Sending request with incorrect HTTP method | GET | Same as TC-USER-01 | pm.test("Status code is 405 or 503", function () { pm.expect(pm.response.code).to.be.oneOf([405, 503]); }); | 1. Open Postman2. Send GET instead of POST | Status 405 Method Not Allowed or 503 Service Unavailable | Status 200 OK. | FAIL | BUG-USER-01-06
|  | TC-USER-01-07 | Verify structure of response on successful registration | POST | Same as TC-USER-01 | pm.test("Response has required fields", function () { const res = pm.response.json(); pm.expect(res).to.have.property("user"); pm.expect(res.user).to.have.property("_id"); pm.expect(res.user).to.have.property("firstName", "Test"); pm.expect(res.user).to.have.property("lastName", "User"); pm.expect(res.user).to.have.property("email", "nagham22@gmail.com"); pm.expect(res).to.have.property("token"); | 1. Send valid POST request 2. Add script to check response structure | passed Response has required fields | As Expected | PASS | —
|  | TC-USER-01-08 | Verify firstName does'nt special characters | POST | { "firstName": "@!!@!", "lastName": "Valid", "email": "valid@mail.com", "password": "Pass1234" } | pm.test("First name allows special characters", function () { pm.expect(pm.response.code).to.eql(400); }); | Send request with special chars in firstName | 201 created | 201 created | PASS | —
|  | TC-USER-01-09 | Verify firstName over 20 characters | POST | { "firstName": "ThisIsAVeryLongNameOverLimit", "lastName": "User", "email": "long@mail.com", "password": "Pass1234" } | pm.test("First name allows special characters", function () { pm.expect(pm.response.code).to.eql(400); }); | Send request with long firstName | Should return 400 Bad Request | As Expected | PASS | —
|  | TC-USER-01-10 | Send Request with invalid body | POST | { "firstName": "Test", "lastName": "User", "emailll": "Nagham222222@gmail.com", "passworddd": "Password123" } | pm.test("Status code is 400", function () { pm.response.to.have.status(400); }); | 1. Open Postman2. Send Post method with invalid body | 400Bad Request | As Expected | PASS | —
|  | TC-USER-01-11 | Verify new user appears in UI after API add | POST | { "firstName": "UIMap", "lastName": "Check", "email": "mapcheck1@ui.com", "password": "Test123!" } | — | 1. Send POST request to create user. 2. Log in from UI using the same email. | Log in from UI using the same email successfully | As Expected | PASS | —
TS-USER-02 | Get User Profile | TC-USER-02-01 | Verify successful retrieval of user profile with valid token | GET | — | pm.test("Status code is 200", function () { pm.response.to.have.status(200); }); | 1. Open Postman 2. Send GET request to /users/me with valid token in Authorization header | Status 200 OK | As Expected | PASS | —
|  | TC-USER-02-02 | Verify response includes correct user fields | GET | — | pm.test("Response has user details", function () { const res = pm.response.json(); pm.expect(res).to.have.property("_id"); pm.expect(res).to.have.property("firstName"); pm.expect(res).to.have.property("lastName"); pm.expect(res).to.have.property("email"); }); | 1. Send GET /users/me with valid token | Response includes id,firstName, lastName, email | As Expected | PASS | —
|  | TC-USER-02-03 | Verify behavior with no token | GET | — | pm.test("Status code is 401", function () { pm.response.to.have.status(401); }); | 1. Send GET /users/me without Authorization header | Status 401 Unauthorized | As Expected | PASS | —
|  | TC-USER-02-04 | Verify behavior with No/invalid/expired token | GET | — | pm.test("Status code is 401", function () { pm.response.to.have.status(401); }); | 1. Send GET /users/me with invalid token | Status 401 Unauthorized | As Expected with Error msg | PASS | —
|  | TC-USER-02-05 | Validate response time is under 500ms | GET | — | pm.test("Response time is less than 500ms", function () { pm.expect(pm.response.responseTime).to.be.below(500); }); | 1. Send GET /users/me with valid token | Response time < 700ms | As Expected | PASS | —
|  | TC-USER-02-06 | Check error when accessing wrong endpoint | GET | — | pm.test("Status code is 404 or 503", function () { pm.expect(pm.response.code).to.be.oneOf([404, 503]); }); | 1. Send GET to /user instead of /users/me | Status 404 Not Found or 503 Service Unavailable | Status 200 OK. | FAIL | BUG-USER-02-06
|  | TC-USER-02-07 | Verify method not allowed for POST | POST | — | pm.test("Status code is 405", function () { pm.response.to.have.status(405); }); | 1. Send POST to /users/me | Status 405 Method Not Allowed | 503Service Unavailable | FAIL | BUG-USER-02-07
TS-USER-03 | Update User | TC-USER-03-01 | Verify updating user with all valid fields | PATCH | { "firstName": "Updated", "lastName": "Username", "email": "test233333@fake.com", "password": "myNewPassword" } | pm.test("Status code is 200", function () { pm.response.to.have.status(200); }); | 1. Open Postman2. Set Authorization header to Bearer {{token}}3. Send PATCH to /users/me with full valid body | Status 200 ok, response contains updated user details | As Expected | PASS | —
|  | TC-USER-03-02 | Update only one field (e.g., firstName only) | PATCH | { "firstName": "ChangedName" } | pm.test("Status code is 200", function () { pm.response.to.have.status(200); }); | 1. Set Authorization header2. Send PATCH request with one valid field | Status 200 ok, response contains updated field | As Expected | PASS | —
|  | TC-USER-03-03 | Update with empty body | PATCH | {} | pm.test("Status code is 200", function () { pm.response.to.have.status(200); }); | 1. Set Authorization header2. Send PATCH request with empty body | Status 200 OK, no fields changed | As Expected | PASS | —
|  | TC-USER-03-04 | Update with invalid email format | PATCH | { "email": "test.com" } | pm.test("Status code is 400", function () { pm.response.to.have.status(400); }); | 1. Set Authorization header2. Send PATCH with invalid email | Status 400 Bad Request | As Expected | PASS | —
|  | TC-USER-03-05 | Update without Authorization token | PATCH | { "firstName": "Hacker" } | pm.test("Status code is 401", function () { pm.response.to.have.status(401); }); | 1. Remove Authorization header2. Send PATCH request | Status 401 Unauthorized | Status 401 Unauthorized with error msg | PASS | —
|  | TC-USER-03-06 | Response time check under 700ms | PATCH | { "firstName": "SpeedTest" } | pm.test("Response time is under 700ms", function () { pm.expect(pm.response.responseTime).to.be.below(700); }); | 1. Set Authorization header2. Send valid PATCH request | Response time < 200ms | As Expected | PASS | —
|  | TC-USER-03-07 | Incorrect endpoint used | PATCH | { "firstName": "WrongPath" } | pm.test("Status code is 404", function () { pm.response.to.have.status(404); }); | 1. Use incorrect URL /user/me instead of /users/me | Status 404 Not Found | 503 Service Unavailable | FAIL | BUG-USER-03-07
|  | TC-USER-03-08 | Update user with special characters in firstName | PATCH | {"firstName": "@@@", "lastName": "User", "email": "test3@fake.com", "password": "Password123"} | pm.test("Should reject special characters in firstName", function () { pm.expect(pm.response.code).to.be.oneOf([400, 422]); pm.expect(pm.response.text()).to.include("firstName"); }); | 1. open postman , 2. send patch reqest with just special chars in the firstname | Status 400 Bad request | As Expected | PASS | —
|  | TC-USER-03-09 | Update user with field values exceeding 20 characters | PATCH | {"firstName": "aaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaa", "lastName": "User", "email": "test@fake.com", "password": "Password123"} | pm.test("Last name too long", function () { pm.expect(pm.response.code).to.equal(400); pm.expect(pm.response.text()).to.include("firstname"); }); | 1. open postman , 2. send patch reqest with more that 20 cars in the name | Status 400 Bad request | As Expected | PASS | —
|  | TC-USER-03-10 | Verify UI reflects updated user info after PATCH | PATCH | { "firstName": "Test", "lastName": "User", "email": "testtest11@fake.com", "password": "myPassword" } | Validate updated fields | 1. Update user via API. 2. Refresh UI Profile page.3. Try ro login with the new updated email | successfully login | successfully login | PASS | —
TS-USER-04 | Login User | TC-USER-04-01 | Verify user login with valid credentials | POST | { "email ": "hla26@gmail.com" , "password" :"myPassword" } | pm.test("Status code is 200", function () { pm.response.to.have.status(200); }); | 1. Open Postman 2. Send POST request to /users/login with valid body | Status 200 OK , and token is in response . | As Expected | PASS | —
|  | TC-USER-04-02 | verify login with invalid email format | POST | { "email ": "hla26.gmail.com" , "password" :"myPassword" } | pm.test("Status code is 400", function () { pm.response.to.have.status(400); }); | 1. Open Postman 2. Send POST request to /users/login with invalid email in body | Status 400 Bad Request. | Status 401 Unauthorized | FAIL | BUG-USER-04-01
|  | TC-USER-04-03 | verify login with wrong password | POST | { "email ": "hla26@gmail.com" , "password" :"myPasswordWrong" } | pm.test("Status code is 401", function () { pm.response.to.have.status(401; }); | 1. Open Postman 2. Send POST request to /users/login with wrong password in body | Status 401 Unauthorized | As Expected | PASS | —
|  | TC-USER-04-04 | verify login with unregistered email | POST | { "email ": "test@gmail.com" , "password" :"Password" } | pm.test("Status code is 401", function () { pm.response.to.have.status(401; }); | 1. Open Postman 2. Send POST request to /users/login with unregistered email in body | Status 401 Unauthorized | As Expected | PASS | —
|  | TC-USER-04-05 | verify login with empty email | POST | { "email ": "" , "password" :"myPassword" } | pm.test("Status code is 401", function () { pm.response.to.have.status(401; }); | 1. Open Postman 2. Send POST request to /users/login with empty email in body | Status 401 Unauthorized | As Expected | PASS
|  | TC-USER-04-06 | verify login with empty password | POST | { "email ": "hla26@gmail.com" , "password" :"" } | pm.test("Status code is 401", function () { pm.response.to.have.status(401; }); | 1. Open Postman 2. Send POST request to /users/login with empty password in body | Status 401 Unauthorized | As Expected | PASS
|  | TC-USER-04-07 | Verify login using expired token | POST | { "email ": "hla26@gmail.com" , "password" :"myPassword" } | pm.test("Status code is 401", function () { pm.response.to.have.status(401); }); | 1. Open Postman 2. Send POST request to /users/login with valid body 3.use expired token | Status 401 Unauthorized | As Expected | PASS | —
|  | TC-USER-04-08 | verify token reuse on login | POST | { "email ": "hla26@gmail.com" , "password" :"myPassword" } | const token1 = pm.environment.get("token1"); pm.test("Login 2: Token should be different from first login", function () { pm.expect(response2.token).to.not.eql(token1); }); | 1. Open Postman 2. Send POST request to /users/login with valid body 3.save the token as token1 4. send the request again 5. save the new token as token2 | Status 200 OK | As Expected | PASS | —
|  | TC-USER-04-09 | verify login using GET method | GET | { "email ": "hla26@gmail.com" , "password" :"myPassword" } | pm.test("Status code is 405", function () { pm.response.to.have.status(405); }); | 1. Open Postman 2. Send GET request to /users/login with valid body | Status 405 Method Not Allowed | Status 200 OK | FAIL | BUG-USER-04-02
|  | TC-USER-04-10 | verify response time is less than 700 ms | POST | { "email ": "hla26@gmail.com" , "password" :"myPassword" } | pm.test("Status code is 200", function () { pm.response.to.have.status(200); }); pm.test("Logout response time is under 700ms", function () { pm.expect(pm.response.responseTime).to.be.below(700); }); | 1. Open Postman 2. Send POST request to /users/login with valid body | Status 200 OK , and response time is less than 700 ms | As Expected | PASS | —
|  | TC-USER-04-11 | verify login with deleted user | POST | { "email ": "hla22@gmail.com" , "password" :"myPassword" } | pm.test("Status code is 401", function () { pm.response.to.have.status(401); }); | 1. Open Postman 2. Send DELETE request to /users/me with valid body 3. send POST request to users/login with deleted user credentials | Status 401 Unauthorized | As Expected | PASS | —
TS-USER-05 | Logout User | TC-USER-05-01 | verify valid logout | POST | — | pm.test("Status code is 200", function () { pm.response.to.have.status(200); }); | 1. Open Postman 2. Send POST request to /users/logout 3. Add Authoriztion Header : Bearer {{token}} | Status 200 OK | As Expected | PASS | —
|  | TC-USER-05-02 | verify logout without Authorization | POST | — | pm.test("Status code is 401", function () { pm.response.to.have.status(401); }); | 1. Open Postman 2. Send POST request to /users/logout 3. Remove Authoriztion Header | Status 401 Unauthorized | As Expected | PASS | —
|  | TC-USER-05-03 | verify logout with expired token | POST | — | pm.test("Status code is 401", function () { pm.response.to.have.status(401); }); | 1. Open Postman 2. Send POST request to /users/logout 3. Add expired token in Authoriztion Header | Status 401 Unauthorized | As Expected | PASS | —
|  | TC-USER-05-04 | verify logout with malformed token | POST | token = abc | pm.test("Status code is 401", function () { pm.response.to.have.status(401); }); | 1. Open Postman 2. Send POST request to /users/logout 3. Add malformed token in Authoriztion Header | Status 401 Unauthorized | As Expected | PASS | —
|  | TC-USER-05-05 | verify logout with already logged out token | POST | — | pm.test("Status code is 401", function () { pm.response.to.have.status(401); }); | 1. Open Postman 2. Send POST request to /users/logout 3. Add logged out token in Authoriztion Header | Status 401 Unauthorized | As Expected | PASS | —
|  | TC-USER-05-06 | verify logout with empty token | POST | — | pm.test("Status code is 401", function () { pm.response.to.have.status(401); }); | 1. Open Postman 2. Send POST request to /users/logout 3. Add Authoriztion Header : Bearer (empty value) | Status 401 Unauthorized | As Expected | PASS | —
|  | TC-USER-05-07 | verify logout without adding space between "Bearer" Keyword and the token value | POST | — | pm.test("Status code is 200", function () { pm.response.to.have.status(200); }); | 1. Open Postman 2. Send POST request to /users/logout 3. Add Authoriztion Header : {{token}} | pm.test("Status code is 200", function () { pm.response.to.have.status(200); }); | As Expected | PASS | —
|  | TC-USER-05-08 | verify logout using GET method | GET | — | pm.test("Status code is 405", function () { pm.response.to.have.status(405); }); | 1. Open Postman 2. Send GET request to /users/logout 3. Add Authoriztion Header : Bearer {{token}} | Status 405 Method Not Allowed | Status 200 OK | FAIL | BUG-USER-05-03
|  | TC-USER-05-09 | verify response time is less than 500 ms | POST | — | pm.test("Status code is 200", function () { pm.response.to.have.status(200); }); pm.test("Logout response time is under 500ms", function () { pm.expect(pm.response.responseTime).to.be.below(500); }); | 1. Open Postman 2. Send POST request to /users/logout 3. Add Authoriztion Header : Bearer {{token}} | Status 200 No OK and response time is less than 500 ms | As Expected | PASS | —
TS-USER-06 | Delete User | TC-USER-06-01 | verify valid Deletion | DELETE | — | pm.test("Status code is 200 or 204", function () { pm.expect(pm.response.code).to.be.oneOf([200, 204]); }); | 1. Open Postman 2. Send DELETE request to /users/me 3. Add Authoriztion Header : Bearer {{token}} | 200 Ok OR 204 No Content | 200 OK | PASS | —
|  | TC-USER-06-02 | verify Delete using ID | DELETE | — | pm.test("Status code is 200 or 204", function () { pm.expect(pm.response.code).to.be.oneOf([200, 204]); }); | 1. Open Postman 2. Send DELETE request to /users/me 3. add _id patameter in URL | 200 Ok OR 204 No Content | As Expected | PASS | —
|  | TC-USER-06-03 | verify Delete with expired token | DELETE | — | pm.test("Status code is 401", function () { pm.response.to.have.status(401; }); | 1. Open Postman 2. Send DELETE request to /users/me with valid body 3.use expired token | Status 401 Unauthorized | As Expected | PASS | —
|  | TC-USER-06-04 | verify Delete with malformed token | DELETE | — | pm.test("Status code is 401", function () { pm.response.to.have.status(401; }); | 1. Open Postman 2. Send DELETE request to /users/me 3. Add malformed token in Authoriztion Header | Status 401 Unauthorized | As Expected | PASS | —
|  | TC-USER-06-05 | verify Deleting non-existing user | DELETE | — | pm.test("Status code is 404", function () { pm.response.to.have.status(404; }); | 1. Open Postman 2. Send DELETE request to /users/me 3. Add valid token for deleted user 4. Send the DELETE request again | Status 404 NOT Found | 401 Unauthorized | FAIL | BUG-USER-06-04
|  | TC-USER-06-06 | verify Delete without authorization | DELETE | — | pm.test("Status code is 401", function () { pm.response.to.have.status(401; }); | 1. Open Postman 2. Send DELETE request to /users/me 3. Remove Authoriztion Header | Status 401 Unauthorized | As Expected | PASS | —
|  | TC-USER-06-07 | verify response time is less than 500 ms | DELETE | — | pm.test("Status code is 200", function () { pm.response.to.have.status(200); }); pm.test("Logout response time is under 500ms", function () { pm.expect(pm.response.responseTime).to.be.below(500); }); | 1. Open Postman 2. Send DELETE request to /users/me 3. Add Authoriztion Header : Bearer {{token}} | Status 200 OK and response time is less than 500 ms | As Expected | PASS | —

## Test Cases (Contact)
Test Suite ID | Test Suite Title | Test Case ID | Summary | Method | Request Body | Scripts | Reproduce Steps | Expected Result | Actual Result | Status | Bug. ID
TS-CONTACT-01 | ADD CONTACT | TS-CONTACT-01-1 | Valid Contact – All Fields Filled | post | { "firstName": "John", "lastName": "Doe", "birthdate": "1970-01-01", "email": "jdoe@fake.com", "phone": "8005555555", "street1": "1 Main St.", "street2": "Apartment A", "city": "Anytown", "stateProvince": "KS", "postalCode": "12345", "country": "USA" } | pm.test("Status code is 201", function () { pm.response.to.have.status(201); }); | 1- open postman. 2- get autharization. 3- send POST request to add contact with valid information. | status 201 crreated | As expected | PASS | —
|  | TS-CONTACT-01-2 | Missing Required Field (firstName) | post | { "firstName": "", "lastName": "Doe", "birthdate": "1970-01-01", "email": "jdoe@fake.com", "phone": "8005555555", "street1": "1 Main St.", "street2": "Apartment A", "city": "Anytown", "stateProvince": "KS", "postalCode": "12345", "country": "USA" } | pm.test("Status code is 400", function () { pm.response.to.have.status(400); }); | 1- open postman. 2- get autharization. 3- send POST request to add contact with valid information with out the ( firstName) | status 400 bad bad request | As expected | PASS | —
|  | TS-CONTACT-1-3 | Invalid email format | post | { "firstName": "John", "lastName": "Doe", "birthdate": "1970-01-01", "email": "jdoe@.com", "phone": "8005555555", "street1": "1 Main St.", "street2": "Apartment A", "city": "Anytown", "stateProvince": "KS", "postalCode": "12345", "country": "USA" } | pm.test("Status code is 400", function () { pm.response.to.have.status(400); }); | 1- open postman. 2- get autharization. 3- send POST request to add contact with valid information with invalid email format | status 400 bad bad request | As expected | PASS | —
|  | TS-CONTACT-1-4 | Invalid phone format | post | { "firstName": "John", "lastName": "Doe", "birthdate": "1970-01-01", "email": "jdoe@fake.com", "phone": "A005555555", "street1": "1 Main St.", "street2": "Apartment A", "city": "Anytown", "stateProvince": "KS", "postalCode": "12345", "country": "USA" } | pm.test("Status code is 400", function () { pm.response.to.have.status(400); }); | 1- open postman. 2- get autharization. 3- send POST request to add contact with valid information with invalid phone format | status 400 bad bad request | As expected | PASS | —
|  | TS-CONTACT-1-5 | Invalid country format | post | { "firstName": "John", "lastName": "Doe", "birthdate": "1970-01-01", "email": "jdoe@fake.com", "phone": "8005555555", "street1": "1 Main St.", "street2": "Apartment A", "city": "Anytown", "stateProvince": "KS", "postalCode": "12345", "country": "usa@&" } | pm.test("Status code is 400", function () { pm.response.to.have.status(400); }); | 1- open postman. 2- get autharization. 3- send POST request to add contact with valid information with invalid contry format | status 400 bad request | The contact was created | FAIL | Bug-contact-1-5
|  | TS-CONTACT-1-6 | Invalid pstalcode format | post | { "firstName": "John", "lastName": "Doe", "birthdate": "1970-01-01", "email": "jdoe@fake.com", "phone": "8005555555", "street1": "1 Main St.", "street2": "Apartment A", "city": "Anytown", "stateProvince": "KS", "postalCode": "1aa5", "country": "USA" } | pm.test("Status code is 400", function () { pm.response.to.have.status(400); }); | 1- open postman. 2- get autharization. 3- send POST request to add contact with valid information with invalid postalcode format | status 400 bad bad request | As expected | PASS | —
|  | TS-CONTACT-1-7 | Invalid birthdate format | post | { "firstName": "John", "lastName": "Doe", "birthdate": "1970-01-a@", "email": "jdoe@fake.com", "phone": "8005555555", "street1": "1 Main St.", "street2": "Apartment A", "city": "Anytown", "stateProvince": "KS", "postalCode": "12345", "country": "USA" } | pm.test("Status code is 400", function () { pm.response.to.have.status(400); }); | 1- open postman. 2- get autharization. 3- send POST request to add contact with valid information with invalid birthdate format | status 400 bad bad request | As expected | PASS | —
|  | TS-CONTACT-1-8 | respons time is less than 700ms | post | { "firstName": "John", "lastName": "Doe", "birthdate": "1970-01-01", "email": "jdoe@fake.com", "phone": "8005555555", "street1": "1 Main St.", "street2": "Apartment A", "city": "Anytown", "stateProvince": "KS", "postalCode": "12345", "country": "USA" } | pm.test("Response time is less than 700ms", function () { pm.expect(pm.response.responseTime).to.be.below(700); }); | 1- open postman. 2- get autharization. 3- send POST request to add contact with valid information | response time should less than 700ms | response time is less than 700ms | PASS | —
TS-CONTACT-02 | Get Contacts list | TS-CONTACT-2-1 | Get contact with valid token | Get | — | pm.test("Status code is 200", function () { pm.response.to.have.status(200); }); | 1- open postman. 2- get autharization. 3- send GET request to have the contacts list | response is 200 | As expected | PASS | —
|  | TS-CONTACT-2-2 | Get contact with invalid token | Get | — | pm.test("Status code is 401", function () {pm.response.to.have.status(401); }); | 1- open postman. 2- put invalid token 3- send GET request to have the contacts list | response is 401 | As expected | PASS | —
|  | TS-CONTACT-2-3 | Get contact without token | Get | — | pm.test("Status code is 401", function () {pm.response.to.have.status(401); }); | 1- open postman. 2- send GET request to have the contacts list | response is 401 | As expected | PASS | —
|  | TS-contact-2-4 | The contact fields exist | Get | — | pm.test(" all contacts field are exist ", function () { pm.expect(pm.response.text()).to.include( "_id", "firstName", "lastName", "birthdate", "email", "phone", "street1", "street2", "city", "stateProvince", "postalCode", "country", "owner", "__v"); }); | 1- open postman. 2- send GET request | response is 200 | As expected | PASS | —
|  | TS-CONTACT-2-5 | respons time is less than 250ms | Get | — | pm.test("Response time is less than 200ms", function () { pm.expect(pm.response.responseTime).to.be.below(200); }); | 1- open postman. 2- send GET request | respons time is less than 200ms | As expected | PASS | —
TS-CONTACTS-03 | GET CONTACT | TC-CONTACTS-01-01 | Get all contacts | GET | — | pm.test("Status code is 200 OK", function () { pm.response.to.have.status(200); }); pm.test("Contact list is not empty", function () { const data = pm.response.json(); pm.expect(data.length).to.be.above(0); }); | 1. Open Postman 2. Put the endpoint link in URL box 3. Choose the method GET 4. Click Send | Status 200 OK | Status 200 OK | PASS | —
|  | TC-CONTACTS-01-02 | Get a specific contact, with ID placed directly in the link | GET | — | "pm.test(""Status code is 200 OK"", function () {pm.response.to.have.status(200);});" pm.test("Response has the contact's ID?", function () { const jsonData = pm.response.json(); pm.expect(jsonData).to.have.property("_id");}); | 1. Open Postman 2. Put the endpoint link in URL box 3. Choose the method GET 4. Click Send 5. You will get the contact list, save any contact ID 6. Put the copied ID directly after the URL 7. Click Send again | Status 200 OK | Status 200 OK | PASS | —
|  | TC-CONTACTS-01-03 | Get a specific contact, with ID as a Parameter | GET | — | "pm.test(""Status code is 200 OK"", function () { pm.response.to.have.status(200); });" | 1. Open Postman 2. Put the endpoint link in URL box 3. Choose the method GET 4. Add the parameters: Key=_id, Value= paste the contact ID from the previous TC 5. Click Send | Status 200 OK, Showing only the specified contact ID | Status 200 OK, But showing all the contacts | FAIL | BUG-CONTACTS-01
|  | TC-CONTACTS-01-04 | Get a specific contact, with "firstName" and "lastName" (Which is required to add contact) as a Parameter | GET | — | "pm.test(""Status code is 200 OK"", function () { pm.response.to.have.status(200); });" pm.test("Response has the contact's ID?", function () { const jsonData = pm.response.json(); pm.expect(jsonData).to.have.property("firstName"); pm.expect(jsonData).to.have.property("lastName"); }); | 1. Open Postman 2. Put the endpoint link in URL box 3. Choose the method GET 4. Add the parameters 5. Click Send | Status 200 OK, Showing only the specified first and last name contact | Status 200 OK, But showing all the contacts | FAIL | BUG-CONTACTS-02
|  | TC-CONTACTS-01-05 | Get a contact that doesn't exist | GET | — | "pm.test(""Status code is 200 OK"", function () { pm.response.to.have.status(200); });" pm.test("Should return 404 for non-existing user", function () { pm.response.to.have.status(404); }); | 1. Open Postman 2. Put the endpoint link in URL box 3. Choose the method GET 4. Paste the saved ID after endpoint URL or add it as an environment var 5. Change the ID last 3 number 6. Click Send | Status 404 Not Found | Status 404 Not Found | PASS | —
|  | TC-CONTACTS-01-06 | Get contact without authorization | GET | — | "pm.test(""Status code is 200 OK"", function () { pm.response.to.have.status(200); });" | 1. Open Postman 2. Put the endpoint link in URL box 3. Choose the method GET 4. Remove the Authorization from Headers or Environment by unchecking the Token 5. Click Send | Status 401 Unauthorized | Status 401 Unauthorized | PASS | —
|  | TC-CONTACTS-01-07 | Get contact with wrong Token | GET | — | "pm.test(""Status code is 200 OK"", function () { pm.response.to.have.status(200); });" | 1. Open Postman 2. Put the endpoint link in URL box 3. Choose the method GET 4. Manipulate the authorization Token from Headers or Environment 5. Click Send | Status 401 Unauthorized | Status 401 Unauthorized | PASS | —
|  | TC-CONTACTS-01-08 | Get contact with wrong endpoint URL | GET | — | "pm.test(""Status code is 200 OK"", function () { pm.response.to.have.status(200); });" | 1. Open Postman 2. Put the endpoint link in URL box 3. Choose the method GET 4. Manipulate the endpoint URL 5. Click Send | Status 404 Not Found | Status 404 Not Found | PASS | —
|  | TC-CONTACTS-01-09 | Get contact with invalid ID | GET | — | pm.test("Should return 400 for wrong or invalid data", function () { pm.response.to.have.status(400); }); | 1. Open Postman 2. Put the endpoint link in URL box 3. Choose the method GET 4. Click Send 5. From response body, copy any Contact ID 6. In the Environment, Create a variable ID and paste the copied ID in the Value box 7. Manipulate the ID value, ex: delete half of it. 8. Go back to request window and click Send | Status 400 Bad Request | Status 400 Bad Request | PASS | —
TS-CONTACTS-04 | UPDATE CONTACT | TC-CONTACTS-02-01 | Update a contact with valid data | PUT | { "firstName": "Mohammad", "lastName": "Badawi", "birthdate": "1993-02-02", "email": "amiller@fake.com", "phone": "8005554242", "street1": "13 School St.", "street2": "Apt. 5", "city": "Washington", "stateProvince": "QC", "postalCode": "A1A1A1", "country": "Canada" } | pm.test("Status is 200 OK", () => { pm.response.to.have.status(200); }); pm.test("firstName updated correctly", () => { const res = pm.response.json(); pm.expect(res.birthdate).to.eql("1993-02-02"); }); | "1. Open Postman 2. Put the endpoint link in URL box with the specified ID 3. Choose the method PUT 4. Write in body > Raw the new data 5. Click Send" | Status 200 OK | Status 200 OK | PASS | —
|  | TC-CONTACTS-02-02 | Update a contact without authorization | PUT | { "firstName": "Mohammad", "lastName": "Badawi", "birthdate": "1994-02-02", "email": "amiller@fake.com", "phone": "8005554242", "street1": "13 School St.", "street2": "Apt. 5", "city": "Washington", "stateProvince": "QC", "postalCode": "A1A1A1", "country": "Canada" } | pm.test("Status is 200 OK", () => { pm.response.to.have.status(200); }); pm.test("firstName updated correctly", () => { const res = pm.response.json(); pm.expect(res.birthdate).to.eql("1994-02-02"); }); pm.test("Should return 401 Unauthorized when token is missing", () => { pm.response.to.have.status(401); }); | "1. Open Postman 2. Put the endpoint link in URL box with the specified ID 3. Choose the method PUT 4. Write in body > Raw the new data 5. Remove the auth token 6. Click Send" | Status 401 Unauthorized | Status 401 Unauthorized | PASS | —
|  | TC-CONTACTS-02-03 | Update a contact with wrong data type | PUT | { "firstName": "12345", "lastName": "67890", "birthdate": "Mohammad", "email": "0566123456", "phone": "Badawi", } | pm.test("Data types are correct", function () { const jsonData = pm.response.json(); pm.expect(jsonData.firstName).to.be.a("string"); pm.expect(jsonData.lastName).to.be.a("string"); pm.expect(jsonData.birthdate).to.be.a("string"); pm.expect(jsonData.email).to.be.a("string"); pm.expect(jsonData.phone).to.be.a("string"); }); | "1. Open Postman 2. Put the endpoint link in URL box with the specified ID 3. Choose the method PUT 4. Write in body > Raw the new data 5. Click Send" | Status 400 Bad Request | Status 400 Bad Request | PASS | —
|  | TC-CONTACTS-02-04 | Update the contact First and Last name with wrong numbers | PUT | { "firstName": "12345", "lastName": "67890" } | pm.test("Status is 200 OK", () => { pm.response.to.have.status(200); }); pm.test("Should return 400 for wrong or invalid data", function () { pm.response.to.have.status(400); }); | "1. Open Postman 2. Put the endpoint link in URL box with the specified ID 3. Choose the method PUT 4. Write in body > Raw the new data 5. Click Send" | Status 400 Bad Request | Status 200 OK | FAIL | —
|  | TC-CONTACTS-02-05 | Update contact data but without first and last name | PUT | "{ ""firstName"": """", ""lastName"": """", ""birthdate"": ""1975-01-01"", ""email"": ""jdoe@fake.com"", ""phone"": ""8005555555"", ""street1"": ""1 Main St."", ""street2"": ""Apartment A"", ""city"": ""Anytown"", ""stateProvince"": ""KS"", ""postalCode"": ""12345"", ""country"": ""USA"" }" | pm.test("Should return 400 for wrong or invalid data", function () { pm.response.to.have.status(400); }); pm.test("firstName and lastName exist in response", function () { var res = pm.response.json(); pm.expect(res).to.have.property("firstName"); pm.expect(res.firstName).to.not.be.null; pm.expect(res.firstName).to.not.be.undefined; pm.expect(res).to.have.property("lastName"); pm.expect(res.lastName).to.not.be.null; pm.expect(res.lastName).to.not.be.undefined; }); | "1. Open Postman 2. Put the endpoint link in URL box with the specified ID 3. Choose the method PUT 4. Write in body > Raw the new data 5. Click Send" | Status 400 Bad Request | Status 400 Bad Request | PASS | —
|  | TC-CONTACTS-02-06 | Update unexsisted contact | PUT | "{ ""firstName"": ""Mohammad"", ""lastName"": ""Badawi"", ""birthdate"": ""1975-01-01"", ""email"": ""jdoe@fake.com"", ""phone"": ""8005555555"", ""street1"": ""1 Main St."", ""street2"": ""Apartment A"", ""city"": ""Anytown"", ""stateProvince"": ""KS"", ""postalCode"": ""12345"", ""country"": ""USA"" }" | pm.test("Status is 200 OK", () => { pm.response.to.have.status(200); }); | "1. Open Postman 2. Put the endpoint link in URL box with the specified ID 3. Choose the method PUT 4. Write in body > Raw the new data 5. Change the contact ID last 3 characters 6. Click Send" | Status 404 Not Found | Status 404 Not Found | PASS | —
|  | TC-CONTACTS-02-07 | Update contact phone with short number | PUT | "{ ""phone"": ""5"" }" | "pm.test(""Status is 200 OK"", () => { pm.response.to.have.status(200); });" pm.response.to.have.status(400);}); | "1. Open Postman 2. Put the endpoint link in URL box with the specified ID 3. Choose the method PUT 4. Write in body > Raw the new data 5. Change the contact phone to be 1 digit 6. Click Send" | Status 400 Bad Request | Status 400 Bad Request | PASS | —
|  | TC-CONTACTS-02-08 | Update contact with invalid email | PUT | { "email": "com.badawi@mohammad" } | pm.test("Status is 200 OK", () => { pm.response.to.have.status(200); }); | "1. Open Postman 2. Put the endpoint link in URL box with the specified ID 3. Choose the method PUT 4. Write in body > Raw the new data 5. Click Send" | Status 400 Bad Request | Status 400 Bad Request | PASS | —
|  | TC-CONTACTS-02-09 | Update contact with NULL data | PUT | { "firstName": "", "lastName": "", "birthdate": "", "email": "", "phone": "" } | pm.test("Should return 400 for wrong or invalid data", function () { pm.response.to.have.status(400); }); pm.test("Response fields are not null", function () { var res = pm.response.json(); pm.expect(res.firstName).to.not.be.null; pm.expect(res.lastName).to.not.be.null; pm.expect(res.birthdate).to.not.be.null; pm.expect(res.email).to.not.be.null; pm.expect(res.phone).to.not.be.null; }); | "1. Open Postman 2. Put the endpoint link in URL box with the specified ID 3. Choose the method PUT 4. Write in body > Raw the NULL data 5. Click Send" | Status 400 Bad Request | Status 400 Bad Request | PASS | —
|  | TC-CONTACTS-02-10 | Update contact with Arabic data | PUT | { "firstName": "محمد", "lastName": "بدوي" } | pm.test("Response fields are not null", function () { var res = pm.response.json(); | "1. Open Postman 2. Put the endpoint link in URL box with the specified ID 3. Choose the method PUT 4. Write in body > Raw the Arabic data 5. Click Send" | Status 200 OK | Status 200 OK | PASS | —
|  | TC-CONTACTS-02-11 | Send an empty body | PUT | NULL | pm.test("Status is 200 OK", () => { pm.response.to.have.status(200); }); | "1. Open Postman 2. Put the endpoint link in URL box with the specified ID 3. Choose the method PUT 4. Delete the body 5. Click Send" | Status 400 Bad Request | Status 400 Bad Request | PASS | —
|  | TC-CONTACTS-02-12 | Update contact with maximum data size | PUT | { "firstName": "MohammadMohammadMohammadMohammad", "lastName": "BadawiBadawiBadawiBadawiBadawi" } | pm.test("Status is 200 OK", () => { pm.response.to.have.status(200); }); | "1. Open Postman 2. Put the endpoint link in URL box with the specified ID 3. Choose the method PUT 4. Add the body 5. Click Send" | Status 400 Bad Request | Status 400 Bad Request | PASS | —
TC-contact-05 | Update Contact Partially | TC-contact-05-01 | Verify the API can update full data | PATCH | { "firstName": "m", "lastName": "m", "birthdate": "1992-05-05", "email": "test@fake.com", "phone": "8005554244", "street1": "44 School St.", "street2": "Apt. 44", "city": "Washingtomm", "stateProvince": "QCmm", "postalCode": "A1A1A5", "country": "Canada5" } | pm.test("Status code is 200", function () { pm.response.to.have.status(200); }); const jsonData = pm.response.json(); pm.test("First name is updated correctly", function () { pm.expect(jsonData.firstName).to.eql("m"); }); pm.test("Last name is updated correctly", function () { pm.expect(jsonData.lastName).to.eql("m"); }); pm.test("Country is not null", function () { pm.expect(jsonData.country).to.not.be.null; }); pm.test("All updated fields are of type string", function () { pm.expect(typeof jsonData.email).to.eql("string"); pm.expect(typeof jsonData.phone).to.eql("string"); pm.expect(typeof jsonData.city).to.eql("string"); }); | 1. Open Postman 2. Log in using POST method 3. Set method to PATCH 4. Fill the URL 5. Go to Body → raw → JSON 6. Fill full data 7. Click Send | The API should update all fields and return the full updated data in the response body with status code 200. The test result should pass. | The API update all fields and return the full updated data in the response body with status code 200. The test result pass. | PASS | —
|  | TC-contact-05-02 | Verify the API can update part of the data | PATCH | { "firstName": "mohammad" } | pm.test("Status code is 200", function () { pm.response.to.have.status(200); }); const jsonData = pm.response.json(); pm.test("First name is updated correctly", function () { pm.expect(jsonData.firstName).to.eql("mohammad"); }); | Same steps asTC-contact-05-01 | The API should update only the specified field and return the full data in the response body with status code 200. The test result should pass. | The API update only the specified field and return the full data in the response body with status code 200. The test result pass. | PASS | —
|  | TC-contact-05-03 | Verify the response time is less than 700 ms when updating part of data | PATCH | { "country": "Canada" } | pm.test("Response time is less than 700ms", function () { pm.expect(pm.response.responseTime).to.be.below(700); }); | Same steps asTC-contact-05-01 | The response time should be under 700 ms. The test result should pass. | The response time less than 700 ms. The test result pass. | PASS | —
|  | TC-contact-05-04 | Check API behavior when request body is empty | PATCH | {} | pm.test("Status code is 200", function () { pm.response.to.have.status(200); }); pm.test("Email remains unchanged", function () { pm.expect(jsonData.email).to.eql("jdoe@fake.com"); }); | Same steps as TC-contact-05-01 but skip filling the request body | The API should return status code 200 without update any field. The test result should pass. | The API return status code 200 without update any field. The test result pass. | PASS | —
|  | TC-contact-05-05 | Update a non-existing contact | PATCH | {} | pm.test("Status code is 404", function () { pm.response.to.have.status(404); }); | Same steps as TC-contact-05-01 with a non-existing ID in URL | The API should return 404 Not Found. The test result should pass. | The API return 404 Not Found. The test result pass. | PASS | —
|  | TC-contact-05-06 | Update without login and without using a token | PATCH | {} | pm.test("Status code is 401", function () { pm.response.to.have.status(401); }); | Same steps as TC-contact-05-01 but do not include token in headers | The API should return 401 Unauthorized and error massage "Please authenticate.". The test result should pass. | The API return 401 Unauthorized and error massage "Please authenticate.". The test result pass. | PASS | —
|  | TC-contact-05-07 | Update from UI and verify from API using GET | GET | — | pm.test("Status code is 200", function () { pm.response.to.have.status(200); }); | 1. Open Contact List App 2. log in by valid credentials 3. Update contact 4. Go to Postman 5. log in using post method 6. Call GET all contacts | The contact data should be updated | The contact data updated | PASS | —
|  | TC-contact-05-08 | Update via API (Postman) and verify in UI | PATCH | { "phone": "0598998811" } | pm.test("Status code is 200", function () { pm.response.to.have.status(200); }); const jsonData = pm.response.json(); pm.test("Phone number updated correctly", function () { pm.expect(jsonData.phone).to.eql("0598998811"); }); | 1. Open Postman 2. Log in using POST method 3. Set method to PATCH 4. Fill the URL with the contact ID 5. Go to Body → raw → JSON 6. Fill updated contact data 7. Click Send 8. Open the Contact List App 9. Log in using valid credentials 10. Verify the updated value appears in the contact list | The contact data should be updated and visible in the UI. | The contact data updated and visible in the UI. | PASS | —
|  | TC-contact-05-09 | Update while leaving required fields blank | PATCH | { "firstName": "", "lastName": "" } | pm.test("Status code is 400", function () { pm.response.to.have.status(400); }); | Same steps as TC-contact-05-01 with empty required fields | The API should return 400 Bad Request due to missing required fields. The test result should pass. | The API return 400 Bad Request due to missing required fields. The test result pass. | PASS | —
|  | TC-contact-05-010 | Verify unchanged fields remain intact after partial update | PATCH | { city": "Nablus" } | pm.test("Status code is 200", function () { pm.response.to.have.status(200); }); | 1. Make a PATCH request with only one field 2. Check full response | Only name should be updated. email, phone, and other fields must remain unchanged. Response should include full updated object. | Only name updated. email, phone, and other fields remain unchanged. | PASS | —
|  | TC-contact-05-011 | Verify the API behavior when updating without specifying the contact ID | PATCH | — | pm.test("Status code is 404", function () {...}) | 1. Open Postman 2. Log in using POST method 3. Set method to PATCH 4. Fill the base URL without appending contact ID 5. Click Send | The API should return status code 404 Not Found. The test result should pass. | 503 Service Unavailable | FAIL | Bug-contact-05-011
|  | TC-contact-05-012 | Update with invalid email format | PATCH | { "email": "amiller@.com" } | pm.test("Status code is 400", function () { pm.response.to.have.status(400); }); | 1. Log in 2. Set method to PATCH 3. Use invalid email format in request 4. Click Send | API should return 400 Bad Request due to invalid email format | 400 Bad Request | PASS | —
|  | TC-contact-05-013 | Update with missing email domain | PATCH | { "email": "amiller@" } | pm.test("Status code is 400", function () { pm.response.to.have.status(400); }); | 1. Open Postman 2. Log in using POST method 3. Set method to PATCH 4. Fill the URL with the contact ID 5. Go to Body → raw → JSON 6. Enter an email missing the domain part 7. Click Send | API should reject invalid email and return 400 | 400 Bad Request | PASS | —
|  | TC-contact-05-014 | Update with invalid phone format | PATCH | { "phone": "abcd1234" } | pm.test("Status code is 400", function () { pm.response.to.have.status(400); }); | 1. Open Postman 2. Log in using POST method 3. Set method to PATCH 4. Fill the URL with the contact ID 5. Go to Body → raw → JSON 6. Enter an invalid phone number 7. Click Send 8. Check the response | API should return 400 for invalid phone format | 400 Bad Request | PASS | —
|  | TC-contact-05-015 | Update with future birthdate | PATCH | { "birthdate": "2050-01-01" } | pm.test("Status code is 400", function () { pm.response.to.have.status(400); }); | 1. Open Postman 2. Log in using POST method 3. Set method to PATCH 4. Fill the URL with the contact ID 5. Go to Body → raw → JSON 6. Enter a future date in the date field 7. Click Send | API should not allow future dates and return 400 | API allow future dates and return 200 | FAIL | Bug-contact-05-015
|  | TC-contact-05-016 | Update with only one valid field | PATCH | { "city": "Nablus" } | pm.test("Status code is 200", function () { pm.response.to.have.status(200); }); | 1. Open Postman 2. Log in using POST method 3. Set method to PATCH 4. Fill the URL with the contact ID 5. Go to Body → raw → JSON 6. Add only one field to update 7. Click Send 8. Verify in the response that all other fields remain unchanged | Only `city` should be updated; other fields remain the same | Only `city` updated; other fields unchanged | PASS | —
|  | TC-contact-05-017 | Update multiple fields partially | PATCH | { "city": "Gaza", "stateProvince": "GA", "postalCode": "12345" } | pm.test("Status code is 200", function () { pm.response.to.have.status(200); }); | 1. Open Postman 2. Log in using POST method 3. Set method to PATCH 4. Fill the URL with the contact ID 5. Go to Body → raw → JSON 6. Enter multiple valid fields to update 7. Click Send | All specified fields should be updated; others stay unchanged | Fields updated correctly | PASS | —
|  | TC-contact-05-018 | Update using uppercase email | PATCH | { "email": "JDOE@FAKE.COM" } | pm.test("Status code is 200", function () { pm.response.to.have.status(200); }); const jsonData = pm.response.json(); pm.test("Email normalized to lowercase", function () { pm.expect(jsonData.email).to.eql("jdoe@fake.com"); }); | 1. Open Postman 2. Log in using POST method 3. Set method to PATCH 4. Fill the URL with the contact ID 5. Go to Body → raw → JSON 6. Enter the email in uppercase letters 7. Click Send | API should accept the email in uppercase and normalize it to lowercase before storing | API accept the email in uppercase and normalize it to lowercase before storing | PASS | —
|  | TC-contact-05-019 | Update with incorrect field name | PATCH | { "citty": "Amman" } | pm.test("Status code is 400", function () { pm.response.to.have.status(400); }); | 1. Open Postman 2. Log in using POST method 3. Set method to PATCH 4. Fill the URL with the contact ID 5. Go to Body → raw → JSON 6. Enter a wrong or misspelled field name ( "ciity" instead of "city") 7. Click Send | API should reject unknown fields with 400 status | The API returned 200 OK, but it didn’t update anything because the field name was wrong. | FAIL | Bug-contact-05-019
|  | TC-contact-05-020 | Update with invalid postal code | PATCH | { "postalCode": "!@#$%" } | pm.test("Status code is 400", function () { pm.response.to.have.status(400); }); | 1. Open Postman 2. Log in using POST method 3. Set method to PATCH 4. Fill the URL with the contact ID 5. Go to Body → raw → JSON 6. Enter invalid characters in the postal code field 7. Click Send 8.Check the response | API should return 400 due to invalid postal code format | 400 Bad Request | PASS | —
|  | TC-contact-05-021 | Update read-only field (ID) | PATCH | { "_id": "123456" } | pm.test("Status code is 400", function () { pm.response.to.have.status(400); }); | 1. Open Postman 2. Log in using POST method 3. Set method to PATCH 4. Fill the URL with the contact ID 5. Go to Body → raw → JSON 6. Attempt to update the ID field 7. Click Send | API should reject update | 400 Bad Request | PASS | —
|  | TC-contact-05-022 | Update birthdate with wrong format | PATCH | { "birthdate": "02-02-1992" } | pm.test("Status code is 400", function () { pm.response.to.have.status(400); }); | 1. Open Postman 2. Log in using POST method 3. Set method to PATCH 4. Fill the URL with the contact ID 5. Go to Body → raw → JSON 6. Enter birthdate in wrong format 7. Click Send | API should require format (YYYY-MM-DD) return 400 | 400 Bad Request | PASS | —
TC-contact-06 | Delete Contact | TC-contact-06-01 | Verify the API deletes a contact correctly | DELETE | {} | pm.test("Status code is 200", function () { pm.response.to.have.status(200); }); pm.test("Check response message is 'Contact deleted'", function () { pm.expect(pm.response.text()).to.eql("Contact deleted"); }); | 1. Open Postman 2. Log in using POST method 3. Set method to DELETE 4. Fill the URL 5. Click Send | The API should delete the contact and return status code 200 and massage "Contact deleted". The test results should pass. | The API delete the contact and return status code 200 and massage "Contact deleted". The test results pass. | PASS | —
|  | TC-contact-06-02 | Verify the API deletes contact in less than 700 ms | DELETE | {} | pm.test("Response time is less than 700ms", function () { pm.expect(pm.response.responseTime).to.be.below(700); }); | Same steps as TC-contact-06-01 | The contact should be deleted successfully and the response time should be under 700 ms. | The contact deleted successfully and the response time under 700 ms. | PASS | —
|  | TC-contact-06-03 | Delete a non-existent contact | DELETE | {} | pm.test("Status code is 404", function () { pm.response.to.have.status(404); }); | Same steps asTC-contact-06-01 with a non-existent ID in URL | The API should return 404 Not Found. The test result should pass. | The API return 404 Not Found. The test result pass. | PASS | —
|  | TC-contact-06-04 | Delete without login and without using a token | DELETE | {} | pm.test("Status code is 401", function () { pm.response.to.have.status(401); }); | Same steps as TC-contact-06-01 but do not include token in headers | The API should return 401 Unauthorized and error massage "Please authenticate.". The test result should pass. | The API return 401 Unauthorized and error massage "Please authenticate.". The test result pass. | PASS | —
|  | TC-contact-06-05 | Delete contact from UI and verify from API using GET | GET | {} | pm.test("Status code is 200", function () { pm.response.to.have.status(200); }); | 1. Open Contact List App 2. log in by valid credentials 3. Delete contact 4. Go to Postman 5. log in using post method 6. Call GET all contacts | The contact should not appear in the API response. | The contact not appear in the API response. | PASS | —
|  | TC-contact-06-06 | Delete via API and verify in UI | DELETE | {} | pm.test("Status code is 200", function () { pm.response.to.have.status(200); }); | 1. Delete contact using DELETE in Postman 2. Open the Contact List App 3. log in with valid credentials 4. Check if the contact has been removed | The contact should no longer appear in the UI. | The contact no longer appear in the UI. | PASS | —
|  | TC-contact-06-07 | Verify the API behavior when deleting without specifying the contact ID | DELETE | {} | pm.test("Status code is 404", function () { pm.response.to.have.status(404); }); | 1. Open Postman 2. Log in using POST method 3. Set method to DELETE 4. Fill the base URL without appending contact ID 5. Click Send | The API should return status code 404 Not Found. The test result should pass. | 503 Service Unavailable | FAIL | Bug-contact-06-07

## Bug Report (User)
Users Module Bug Report
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Method | URL | Request Body | Expected Results | Actual Results | Notes | Visual Proof | Reporter
Bug-User-01-06 | Verify the status of Sending request with incorrect HTTP method | send the Request with GET method insted of POST method | Postman | Medium | Major | 1. Open Postman 2. Send GET to /users instead of POST | GET | https://thinking-tester-contact-list.herokuapp.com/users | { "firstName": "John", "email": "john@example.com" } | Status 405 Method Not Allowed | Status 200 OK |  | https://www.awesomescreenshot.com/image/55622674?key=59ca7f6f886c8cdf6c0e867f7ef95140 | Nagham
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce |  |  |  | Expected Results | Actual Results | Notes | Visual Proof | Reporter
Bug-User-02-06 | Use Incorrect endpoin with GET method | Ensure GET is not accepted on user/me endpoint | Postman | Low | Moderate | 1. Open Postman 2. Send GET req to /user/me endpont | GET | https://thinking-tester-contact-list.herokuapp.com/user/me | - | Status 404 Not found | 200 OK |  | https://www.awesomescreenshot.com/image/55622672?key=e0dd161fc2276c2d4e91003dc64efce8 | Nagham
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce |  |  |  | Expected Results | Actual Results | Notes | Visual Proof | Reporter
Bug-User-02-07 | Verify the Request not allowed for POST method | send the Request With POST method insted of PATCHmethod | Postman | Low | Moderate | 1. Open Postman 2. Send with POST to /users instead of GET | POST | https://thinking-tester-contact-list.herokuapp.com/users/me | - | 405 Method Not Allowed | 503 Service Unavailable |  | https://www.awesomescreenshot.com/image/55622673?key=4f646be4235cc96d9d9e7b2274e46b4e | Nagham
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce |  |  |  | Expected Results | Actual Results | Notes | Visual Proof | Reporter
Bug-User-03-07 | Use Incorrect endpoint with PATCH method | send the Request to use/me insted of users/me with PATCH method | Postman | Low | Moderate | 1. Open Postman 2. Use incorrect endpoint /user/me | PATCH | https://thinking-tester-contact-list.herokuapp.com/use/me | { "firstName": "nagham", "lastName": "Username", "email": "naghamahmad3326212234@fake.com", "password": "myNewPassword" } | 404 Not Found | 503 Service Unavailable |  | https://www.awesomescreenshot.com/image/55622675?key=cd647ad4317071c03a6f44e05b1bde38 | Nagham
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce |  |  |  | Expected Results | Actual Results | Notes | Visual Proof | Reporter
Bug-User-04-01 | POST request with invalid email format returns 401 instead of expected 400 | When sending POST request for login and the email format is invalid, API returns 401 Unauthorized instead if expected status code 400 Bad Request | Postman | Medium | Moderate | 1. Open Postman 2. Send POST request to the endpoint /users/login with invalid email in body 3.click Send |  |  |  | Status Code 400 Bad request | Status Code 401 Unauthorized |  | BUG-USER-04-01 | Hala Mousa
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce |  |  |  | Expected Results | Actual Results | Notes | Visual Proof | Reporter
Bug-User-04-02 | Use GET method for login instead of POST returns 200 OK instead of 405 Method Not Allowed | When login with valid credentials using GET method , API returns 200 OK instead od 405 Method Not Allowed | Postman | High | Moderate | 1. Open Postman 2. Send GET request to /users/login with valid body |  |  |  | Status Code 405 Method Not Allowed | Status Code 200 OK |  | BUG-USER-04-02 | Hala Mousa
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce |  |  |  | Expected Results | Actual Results | Notes | Visual Proof | Reporter
Bug-User-05-03 | Use GET method for logout instead of POST returns 200 OK instead of 405 Method Not Allowed | When logout with valid token using GET method , API returns 200 OK instead od 405 Method Not Allowed | Postman | High | Moderate | 1. Open Postman 2. Send GET request to /users/logout 3. Add Authoriztion Header : Bearer {{token}} |  |  |  | Status Code 405 Method Not Allowed | Status Code 200 OK |  | BUG-USER-05-03 | Hala Mousa
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce |  |  |  | Expected Results | Actual Results | Notes | Visual Proof | Reporter
Bug-User-06-04 | Use DELETE method to delete non-existing user returns 401 Unauthorized instead of 404 Not Found | When attempt to delete a user is alreday deleted , the Api returns 401 unauthorized instead of 404 Not found | Postman | High | Moderate | 1. Open Postman 2. Send DELETE request to /users/me 3. Add valid token for deleted user 4. Send the DELETE request again |  |  |  | Status 404 Not Found | Status Code 401 Unauthorized |  | BUG-USER-06-04 | Hala Mousa

## Bug Reports (Contact)
Contacts Module Bug Report
Bug ID | Title | Summary | Environment | Priority | Severity |  |  |  | Steps to Reproduce | Expected Results | Actual Results | Notes | Visual Proof | Reporter
Bug-Contact-01-05 | Contact is created even when the "country" field contains an invalid value | The API allows the creation of a new contact even when the "country" field contains an invalid or misspelled value. | Postman | Medium | Moderate |  |  |  | 1- open post man 2-add new contact INFO with an invaled name for the contry 3- send the request | Status 400 Bad Request | Status 201 created |  | https://www.awesomescreenshot.com/image/55631624?key=d331a8da41a96900f783d6fd2b8fb378 | Ehab halabi
Bug ID | Title | Summary | Environment | Priority | Severity |  |  |  | Steps to Reproduce | Expected Results | Actual Results | Notes | Visual Proof | Reporter
Bug-Contacts-03-01 | Parameters don't work | The API gives all the contacts even when specifying the contact's ID in the parameters | Postman | High | Major |  |  |  | 1. Open Postman 2. Put the endpoint link in URL box 3. Choose the method GET 4. Add the parameters: Key=_id, Value= paste the contact ID from the previous TC 5. Click Send | Status 200 OK, Showing only the specified contact ID | Status 200 OK, But showing all the contacts |  | https://www.awesomescreenshot.com/image/55639305?key=1b2e8d872b7c93d4a0052c4438ec43db | Badawi
Bug ID | Title | Summary | Environment | Priority | Severity |  |  |  | Steps to Reproduce | Expected Results | Actual Results | Notes | Visual Proof | Reporter
Bug-Contacts-03-02 | Parameters don't work | The API gives all the contacts even when specifying the contact's First and Last names which is required, in the parameters | Postman | High | Major |  |  |  | 1. Open Postman 2. Put the endpoint link in URL box 3. Choose the method GET 4. Add the parameters 5. Click Send | Status 200 OK, Showing only the specified first and last name contact | Status 200 OK, But showing all the contacts |  | https://www.awesomescreenshot.com/image/55639306?key=374b79b058f9ee84f0192336364ae5ec | Badawi
Bug ID | Title | Summary | Environment | Priority | Severity |  |  |  | Steps to Reproduce | Expected Results | Actual Results | Notes | Visual Proof | Reporter
Bug-Contacts-04-01 | Wrong data validation | The API updated the specified contact's first and last names with numbers | Postman | Critical | Major |  |  |  | "1. Open Postman 2. Put the endpoint link in URL box with the specified ID 3. Choose the method PUT 4. Write in body > Raw the new data 5. Click Send" | Status 400 Bad Request | Status 200 OK |  | https://www.awesomescreenshot.com/image/55639307?key=4c5f83961d3b8cb2e95f17eb8c208388 | Badawi
Bug ID | Title | Summary | Environment | Priority | Severity | METHOD | URL | Request Body | Steps to Reproduce | Expected Results | Actual Results | Notes | Visual Proof | Reporter
Bug-contact-05-015 | PATCH request allows updating birthdate to a future date instead of rejecting it | When sending a PATCH request to update birthdate with a future date (2050-01-01), the API accepts it and returns 200 OK instead of 400 Bad Request. | Postman | Medium | Moderate | PATCH | https://thinking-tester-contact-list.herokuapp.com/contacts/{{contact_id}} | { "birthdate": "2050-01-01" } | 1. Open Postman 2. Log in using POST method 3. Set method to PATCH 4. Fill the URL with the contact ID 5. Go to Body → raw → JSON 6. Enter a future date in the date field 7. Click Send | API should not allow future dates and return 400 Bad Request | API allows future dates and returns 200 OK |  | https://www.awesomescreenshot.com/image/55600761?key=db066c47e4a240d0a70f82136b0a203d | Foqahaa
Bug ID | Title | Summary | Environment | Priority | Severity | METHOD | URL | Request Body | Steps to Reproduce | Expected Results | Actual Results | Notes | Visual Proof | Reporter
Bug-contact-05-019 | PATCH request with incorrect field name returns 200 OK instead of 400 Bad Request | When sending a PATCH request with wrong field name ('citty'), the API returns 200 OK but ignores the update. It should return 400 Bad Request. | Postman | Medium | Moderate | PATCH | https://thinking-tester-contact-list.herokuapp.com/contacts/{{contact_id}} | { "citty": "Amman" } | 1. Open Postman 2. Log in using POST method 3. Set method to PATCH 4. Fill the URL with the contact ID 5. Go to Body → raw → JSON 6. Enter a wrong or misspelled field name ( "ciity" instead of "city") 7. Click Send | API should reject unknown fields with 400 status | The API returned 200 OK, but it didn’t update anything because the field name was wrong. |  | https://www.awesomescreenshot.com/image/55600831?key=bd5e0fb776493dfe081daa16fd21a03c | Foqahaa
Bug ID | Title | Summary | Environment | Priority | Severity | METHOD | URL | Request Body | Steps to Reproduce | Expected Results | Actual Results | Notes | Visual Proof | Reporter
Bug-contact-05-011 | PATCH request without Contact ID returns 503 instead of expected 404 Not Found | When attempting to update a contact using a PATCH request without specifying a contact ID in the URL, the API returns a 503 Service Unavailable status instead of the expected 404 Not Found. | Postman | Medium | Major | PATCH | https://thinking-tester-contact-list.herokuapp.com/contacts | {} | 1. Open Postman 2. Log in using POST method 3. Set method to PATCH 4. Fill the base URL without appending contact ID 5. Click Send | API should return 404 Not Found. The test should pass. | API returns 503 Service Unavailable. The test fails. |  | https://www.awesomescreenshot.com/image/55583164?key=cfcd1dfad397535f5092cc9870ec26e3 | Foqahaa
Bug ID | Title | Summary | Environment | Priority | Severity | METHOD | URL | Request Body | Steps to Reproduce | Expected Results | Actual Results | Notes | Visual Proof | Reporter
Bug-contact-06-07 | DELETE request without Contact ID returns 503 instead of expected 404 Not Found | When attempting to delete a contact using a DELETE request without specifying a contact ID in the URL, the API returns a 503 Service Unavailable status instead of the expected 404 Not Found. | Postman | Medium | Major | PATCH | https://thinking-tester-contact-list.herokuapp.com/contacts/{{contact_id}} | {} | 1. Open Postman 2. Log in using POST method 3. Set method to DELETE 4. Fill the base URL without appending contact ID 5. Click Send | API should return status code 404 Not Found. The test result should pass. | API returns 503 Service Unavailable. |  | https://www.awesomescreenshot.com/image/55601577?key=e300ba8a07093493f46edb55a1bbc4fe | Foqahaa

## RTM
Requirement Traceability Matrix (RTM)
Req ID | Requirement Name | Reuirement Description | Test Suite ID | Assigned To | Current Status
Req-01 | Add Contact | The API should allow the user to add a new contact by providing details such as name, phone, email, address, and birthdate. If the data is valid, the contact will be created and returned with a unique ID. | TS-contact-01 | Ehab Halabi | PASS
Req-02 | Get Contact List | The API should return the full list of contacts for the logged-in user. | TS-contact-02 | Ehab Halabi | PASS
Req-03 | Get Contact | The API must bring the user the contact's data he/she requests, the data must be correct, and meets the expected validation criteria with no missing or wrong data | TS-Contact-03 | Badawi | PASS
Req-04 | Update Contact | The user should be able to edit, update or fix a contact's data easily by sending API request to the database. The API must update the right record supported by the user. | TS-Contact-04 | Badawi | PASS
Req-05 | Update Contact Partially | The API should support partial updates to a contact Only the fields sent in the PATCH request will be modified, others should stay the same. | TS-Contact-05 | Foqahaa | PASS
Req-06 | Delete Contact | The API should delete the specified contact when a valid contact ID is provided. | TS-Contact-06 | Foqahaa | PASS
Req-07 | Add User | API should Add a user with valid feilds | TS-USER-01 | Nagham | PASS
Req-08 | Get User Profile | API should be able to returnthe user information | TS-USER-02 | Nagham | PASS
Req-09 | Update User | API should UPDATE user information with valid fields | TS-USER-03 | Nagham | PASS
Req-10 | Log In User | The API should log out the user and invalidate the authentication token. | TS-USER-04 | Hala Mousa | PASS
Req-11 | Log Out User | The API should log in the user using valid credentials and return an authentication token. | TS-USER-05 | Hala Mousa | PASS
Req-12 | Delete User | The API should delete the user’s account and all related data after confirmation. | TS-USER-06 | Hala Mousa | PASS

## Test Summary Report
Test Report
Test Cycle | System Test
Executed | Passed |  |  | 100
| Failed |  |  | 18
| Total Tests Executed (Passed + Failed) |  |  |  |  | 118
Pending | [5 empty] | 0
In Progress | [5 empty] | 0
Blocked | [5 empty] | 0
(Sub-Total) Test Planed | [5 empty] | 118
[Pending - In Progress - Blocked - Test Executed]
Functions (Test Scenarios) | Description | TCs Excuted % | TCs Passed % | TCs pending | Priority | Remarks
Add Contact | The API should allow the user to add a new contact by providing details such as name, phone, email, address, and birthdate. If the data is valid, the contact will be created and returned with a unique ID. | 100% | 75% | 0% | High
Get Contact List | The API should return the full list of contacts for the logged-in user. | 100% | 100% | 0% | High
Get Contact | The API must bring the user the contact's data he/she requests, the data must be correct, and meets the expected validation criteria with no missing or wrong data | 100% | 78% | 0% | High
Update Contact | The user should be able to edit, update or fix a contact's data easily by sending API request to the database. The API must update the right record supported by the user. | 100% | 92% | 0% | High
Update Contact Partially | The API should support partial updates to a contact Only the fields sent in the PATCH request will be modified, others should stay the same. | 100% | 86% | 0% | High
Delete Contact | The API should delete the specified contact when a valid contact ID is provided. | 100% | 85.7% | 0% | High
Add User | API should Add user with valid fields | 100% | 81% | 0% | High
Get User Profile | API should return user profile correctly | 100% | 71% | 0% | High
Update User | API should UPDATE user information with valid fields | 100% | 90% | 0% | High
Log Out User | The API Should support only authorized user logout | 100% | 89% | 0% | High
Log In User | The API Should support only authorized user login | 100% | 82% | 0% | High
Delete User | The API should support deleteing existing user with authorization | 100% | 86% | 0% | High
| Run Collection (USER) | [5 empty] | Run Collection (CONTACT)